## Slide 1: Value Summary & Mutual Success Plan “Project XYZ”
Full Benefits Possible By
01/01/26
Possible Transition By
01/07/25
Go - Live Possible By
01/10/25
Needed Decision By
01/06/25
Possible Time Frame
Project | XYZ
Sponsor | CxO Comapny
Description | Assessment of necessity and economic efficiency
Current Situation | Cost of Inaction | Who is Suffering?
No central governance & proactive management in the area of XYZ | Missed financial savings | COMPANY Group
 | Risk of data leakage | Employees, customers, suppliers
 | Threat of a penalty payment | COMPANY Management Board
Desired Future State | Projected Benefits of Change | Who Will Benefit?
Complete SOLUTION through “Global Process Solution” with automated processes, a central Governance structure and clear rules of engagement | Leveraging cost savings | COMPANY Group
 | Risk of data leakage minimized | Employees, customers, suppliers
 | Potential penalties eliminated | COMPANY Management Board
Priorities & Initiatives
Step 1: Assessment of the current situation Step 2: Concept development & presentation Step 3: Evaluation and decision
Status
Step 1: Assessment of the current situation completed Step 2: High-Level Concept development & presentation done Next Step: Obtain an opinion from the COMPANY data protection experts and nominate a sponsor until…